## Sheet1
Bladeless Fan Burndown Chart
Project | Story | Task | Start | 27/5 | 28/5 | 29/5 | 30/5 | 31/5 | 1/6 | 2/6 | 3/6 | 4/6 | 5/6 | 6/6 | 7/6
Bladeless Fan | Persiapan | Instalasi App | 4 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Bladeless Fan | Persiapan | Cari sumber info | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Bladeless Fan | Persiapan | Burndown Chart | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
Bladeless Fan | Presentasi | Halaman utama | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Bladeless Fan | Presentasi | History | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
Bladeless Fan | Presentasi | Latar belakang | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
Bladeless Fan | Presentasi | Cara kerja | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 3 | 2 | 0
Bladeless Fan | Presentasi | Keuntungan produk | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0
Bladeless Fan | Presentasi | Video presentasi | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Bladeless Fan | Finishing | Finishing | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4
Ideal - Remaining efforts in uninterrupted working hours |  |  | 36 | 33 | 30 | 27 | 24 | 21 | 18 | 15 | 12 | 9 | 6 | 3 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  | 36 | 30 | 27 | 27 | 23 | 21 | 17 | 15 | 12 | 6 | 0 | 0 | 0
Note on F4: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered